## Wx
PROJECT REPORT
Group | 3
Week | 06/09/2022-17/09/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Web Skeleton (HTML, CSS, JS files) | Completed
2 | SRS Template | In Progress
| Design Document | In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Web Skeleton (HTML, CSS, JS files) | TrungPH
2 | SRS Tenplate | NamNT, DucDH
3 | Design Document | HyTDM, KietDT
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
Pending
Pending
Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | SRS Document (Part II) | 2022-01-10
2 | Design Document (Part II, III) | 2022-01-10
3 | Backend | 2022-01-10
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C17: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue